## Deliverables, Ethics, DMP, Othe
Deliverables, Ethics, DMP, Other Reports for Project 730027
Deliverables, Ethics, DMP, Other Reports
| WP No | Del Rel. No | Del No | Title | Description | Lead Beneficiary | Nature | Dissemination Level | Est. Del. Date (annex I) | Rev. Due Date | Receipt Date | Approval Date | Status
| WP1 | D1.1 | D1 | Project meetings and workshops | List of project meetings and workshops, with pointer to related information on the intranet or web site (agenda, registration/participant list, presentations, minutes) | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 23 Sep 2021 |  | Submitted
| WP1 | D1.2 | D45 | Report on cumulative expenditure incurred after Year 1 | Report on cumulative expenditure incurred after Year 1 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2017 |  | 10 Oct 2019 |  | Submitted
| WP1 | D1.3 | D46 | Report on cumulative expenditure incurred after Year 2 | Report on cumulative expenditure incurred after Year 2 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2018 |  | 10 Oct 2019 |  | Submitted
| WP1 | D1.4 | D50 | Progress report at M36 | Progress report at M36, as provided by the Grant Agreement article 19.1 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2019 |  | 29 Nov 2019 |  | Submitted
| WP1 | D1.5 | D47 | Report on cumulative expenditure incurred after Year 3 | Report on cumulative expenditure incurred after Year 3 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2019 |  | 12 Mar 2020 |  | Submitted
| WP1 | D1.6 | D48 | Report on cumulative expenditure incurred after Year 4 | Report on cumulative expenditure incurred after Year 4 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2020 |  | 11 Jan 2021 |  | Submitted
| WP1 | D1.7 | D49 | Report on cumulative expenditure incurred after Year 5 | Report on cumulative expenditure incurred after Year 5 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  |  |  | Pending
| WP1 | D1.8 | D51 | Report on cumulative expenditure incurred after Year 6 | Report on cumulative expenditure incurred after Year 6 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2022 |  |  |  | Pending
| WP2 | D2.1 | D2 | JTC 2017 call documents (public part) | JTC 2017 call documents (public part): Call page, call announcement, proposal form | ANR | Report | Public | 31 Dec 2016 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP2 | D2.2 | D3 | JTC 2017 call documents (non public part) | JTC 2017 call documents (non public part): Memorandum of Understanding, Procedures of the Call | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2016 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP2 | D2.3 | D4 | JTC 2017 networking event | JTC 2017 networking event agenda, registration / participant lists and presentations | MINECO | Report | Public | 31 Jan 2017 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP3 | D3.1 | D5 | JTC 2017 pre-proposal evaluation outcome | JTC 2017 pre-proposal evaluation outcome: Consensus reports and rankings | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Mar 2017 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP3 | D3.2 | D6 | JTC 2017 pre-proposal selection outcome | JTC 2017 pre-proposal selection outcome: List of pre-proposals invited to submit a full proposal | ANR | Report | Public | 30 Apr 2017 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP3 | D3.3 | D7 | JTC 2017 full proposal evaluation outcome | JTC 2017 full proposal evaluation outcome: Consensus reports and rankings | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Sep 2017 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP3 | D3.4 | D8 | JTC 2017 full proposal selection outcome | JTC 2017 full proposal selection outcome: List of projects recommended for funding | ANR | Report | Public | 31 Oct 2017 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP4 | D4.1 | D9 | JTC 2017 project periodic reports and reviews for Period 1 | JTC 2017 project periodic reports and reviews for Period 1 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Jun 2019 |  | 15 Nov 2019 |  | Submitted
| WP4 | D4.2 | D10 | JTC 2017 project periodic reports and reviews for Period 2 | JTC 2017 project periodic reports and reviews for Period 2 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Jun 2020 |  | 07 Jul 2020 |  | Submitted
| WP4 | D4.3 | D11 | JTC 2017 project periodic reports and reviews for Period 3 | JTC 2017 project periodic reports and reviews for Period 3 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Jul 2022 |  |  |  | Pending
| WP4 | D4.4 | D12 | JTC 2017 assessment | JTC 2017 outcome analysis report, including possible recommendations | AEI | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2022 |  |  |  | Pending
| WP5 | D5.1 | D14 | Web site and intranet administration manuals | Web site and intranet administration manuals | F.R.S.-FNRS | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP5 | D5.2 | D13 | Description of website content | Description of the website content. The content is continuously updated and a document summarising the produced content over the project duration is delivered at the end of the project. | F.R.S.-FNRS | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP5 | D5.3 | D15 | Communication toolkit for the JTC 2017 launch | Communication toolkit for the JTC 2017 launch | F.R.S.-FNRS | Websites, patents filing, etc. | Public | 31 Dec 2016 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP5 | D5.4 | D16 | Promotion plan for the JTC 2017 publication | Promotion plan for the JTC 2017 publication | F.R.S.-FNRS | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2016 |  | 16 Jul 2018 | 14 Aug 2018 | Approved
| WP6 | D6.1 | D17 | Graphene Flagship Liaison Group meetings | Graphene Flagship Liaison Group meetings: List of meetings with agenda, participant list, presentations and minutes | VR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP6 | D6.2 | D18 | Landscape inventory 2019 in the domain of the Graphene Flagship | Inventory of projects and programmes in the domain of the Graphene Flagship | VINNOVA | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Mar 2018 |  | 29 Nov 2019 |  | Submitted
| WP6 | D6.3 | D19 | Strategic analysis 2019 in the domain of the Graphene Flagship | Strategic analysis of the gaps and overlaps in the domain of the Graphene Flagship | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2018 |  | 28 Nov 2019 |  | Submitted
| WP6 | D6.4 | D20 | Landscape inventory 2021 in the domain of the Graphene Flagship | Inventory of projects and programmes in the domain of the Graphene Flagship | VINNOVA | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Sep 2021 |  | 30 Sep 2021 |  | Pending
| WP6 | D6.5 | D21 | Strategic analysis 2021 in the domain of the Graphene Flagship | Analysis of gaps and overlaps in the domain of the Graphene Flagship | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP6 | D6.6 | D22 | International collaboration funding opportunities for the Graphene Flagship | International collaboration funding opportunities for the Graphene Flagship: Report summarising the international collaboration funding opportunities for researchers in the Graphene Flagship identified in FLAG-ERA | AEI | Report | Public | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP7 | D7.1 | D23 | HBP Liaison Group meetings | HBP Liaison Group meetings: List of meetings with agenda, participant list, presentations and minutes | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP7 | D7.2 | D24 | Landscape inventory 2019 in the domain of the HBP | Inventory of projects and programmes in the domain of the HBP | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Mar 2018 |  | 31 Oct 2019 |  | Submitted
| WP7 | D7.3 | D25 | Strategic analysis 2019 in the domain of the HBP | Strategic analysis of the gaps and overlaps in the domain of the HBP | NWO | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2018 |  | 31 Oct 2019 |  | Submitted
| WP7 | D7.4 | D26 | Landscape inventory 2021 in the domain of the HBP | Inventory of projects and programmes in the domain of the HBP | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Sep 2021 |  | 30 Sep 2021 |  | Submitted
| WP7 | D7.5 | D27 | Strategic analysis 2021 in the domain of the HBP | Analysis of gaps and overlaps in the domain of the HBP | NWO | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP7 | D7.6 | D28 | International collaboration funding opportunities for the HBP | International collaboration funding opportunities for the HBP: Report summarising the international collaboration funding opportunities for researchers in the HBP identified in FLAG-ERA | AEI | Report | Public | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP8 | D8.1 | D29 | JTC 2016 project periodic reports and reviews for Period 1 | JTC 2016 project periodic reports and reviews for Period 1 | MIUR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2019 |  | 26 Nov 2019 |  | Submitted
| WP8 | D8.2 | D30 | JTC 2016 projects seminar 1 presentations | JTC 2016 projects seminar 1 presentations | MIUR | Report | Public | 30 Nov 2019 |  | 26 Nov 2019 |  | Submitted
| WP8 | D8.3 | D31 | JTC 2016 project periodic reports and reviews for Period 2 | JTC 2016 project periodic reports and reviews for Period 2 | MIUR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2019 |  | 26 Nov 2019 |  | Submitted
| WP8 | D8.4 | D32 | JTC 2016 projects seminar 2 presentations | JTC 2016 projects seminar 2 presentations | MIUR | Report | Public | 30 Nov 2019 |  | 26 Nov 2019 |  | Submitted
| WP8 | D8.5 | D33 | JTC 2016 project periodic reports and reviews for Period 3 | JTC 2016 project periodic reports and reviews for Period 3 | MUR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP8 | D8.6 | D34 | JTC 2016 projects seminar 3 presentations | JTC 2016 projects seminar 3 presentations | MIUR | Report | Public | 30 Nov 2021 |  | 28 Apr 2020 |  | Submitted
| WP8 | D8.7 | D35 | JTC 2016 assessment | JTC 2016 outcome analysis report, including possible recommendations | MUR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP9 | D9.1 | D36 | JTC 2015 project periodic reports and reviews for Period 1 | JTC 2015 project periodic reports and reviews for Period 1 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2020 |  | 27 Nov 2020 |  | Submitted
| WP9 | D9.2 | D37 | JTC 2015 project periodic reports and reviews for Period 2 | JTC 2015 project periodic reports and reviews for Period 2 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2020 |  | 27 Nov 2020 |  | Submitted
| WP9 | D9.3 | D38 | JTC 2015 project periodic reports and reviews for Period 3 | JTC 2015 project periodic reports and reviews for Period 3 | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2020 |  | 27 Nov 2020 |  | Submitted
| WP9 | D9.4 | D39 | JTC 2015 assessment | JTC 2015 outcome analysis report, including possible recommendations | FCT | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2020 |  | 21 Dec 2020 |  | Submitted
| WP10 | D10.1 | D40 | Best practices and recommendations about the integration of nationally and regionally funded research in the Flagships | Best practices and recommendations about the integration of nationally and regionally funded research in the Flagships | ANR | Report | Public | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP10 | D10.2 | D41 | Funding opportunities for the Flagships | Funding opportunities for the Flagships | EPSRC | Report | Public | 30 Nov 2021 |  | 2021-01-28 |  | Submitted
| WP10 | D10.3 | D42 | List of associated members | Report on contacts with potential new members and list of associated members at the end of the project | AEI | Report | Public | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
| WP10 | D10.4 | D43 | Evaluation and synthesis of results | Evaluation and synthesis of results | AEI | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2022 |  |  |  | Pending
| WP10 | D10.5 | D44 | Recommendations for the FET Flagship next phases | Recommendations from the NRFOs for the FET Flagship next phases | ANR | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2021 |  | 30 Nov 2021 |  | Submitted
13